## Project Team Directory: SDG 3 Analysis

Project: SDG-Health Analytics: Life Expectancy Modeling

Institution: IIMSTC Internship

| Role | Assigned Member | Focus Area |
| --- | --- | --- |
| Project Lead / President | Vaastav | Milestone Management & Daily Coordination |
| Vice President / Ops | Rafa | Time Logging & Blocker Resolution |
| Data Engineer | Sruthi | Data Sourcing & Cleaning (WHO/Kaggle) |
| EDA Specialist | Avinash, Vaastav | Visualizing Trends & Statistical Analysis |
| Feature Engineering | Saayanth & Vrushank | Data Scaling & Indicator Optimization |
| Model Development | Rafa, Sadiya & Mahesh | Regression Implementation & Training |
| Evaluation & Optimization | Ravi & Issa | Accuracy Metrics ($R^2$, RMSE) & Tuning |
| Documentation Lead | Rafa & Vrushank | GitHub Maintenance & Final Report |
| SDG Analytics Report | Manoj & Harshita R | SDG Alignment & Impact Reporting |

## Initial Action Items for the Team

### Phase 1: Setup (Next 24 Hours)

- Vrushank: Create the GitHub Repository and invite the team (ensure everyone accepts their invites).

- Rafa: Set up a shared "Work Log" (Excel/Google Sheets) for the 4–5 hour daily tracking.

- Sruthi & Rafa: Search Kaggle for "Life Expectancy WHO" and upload the raw CSV to the /data folder on GitHub.

## Technical Handoff : From Data to Model

Since the dataset is already sourced and cleaned, the project moves into the Analysis & Feature Pipeline.

### 1. The Sourcing Handoff

- Rafa to Sruthi: Rafa identifies and provides the raw CSV dataset (WHO/World Bank).

- Sruthi to Vrushank: Sruthi cleans the data and Vrushank versions it as cleaned_data.csv on GitHub.

### 2. The Analytical Handoff

- Sruthi to Avinash: Avinash takes the cleaned data to find statistical trends.

- Objective: Identify the strongest predictors of life expectancy (e.g., does Sanitation have a higher correlation than Infant Mortality?).

### 3. The Engineering Handoff

- Avinash to Saayanth: Insights from plots are passed to Saayanth.

- Objective: Saayanth handles Feature Scaling and One-Hot Encoding (converting "Developed/Developing" into numeric values) so the model can read it.

### 4. The Modeling Handoff

- Saayanth to Sadiya: The final, optimized matrix is handed to Sadiya.

- Objective: Sadiya trains the Multiple Linear Regression model.

### 5. The Optimization Handoff

- Sadiya to Ravi: Sadiya passes the model results.

- Objective: Ravi calculates the error metrics (R^2, MAE, RMSE) and suggests tuning to improve accuracy.

## 🛠️ GitHub Strategy for Vrushank

Since Rafa provided the data and Sruthi cleaned it, Vrushank should ensure the following structure is visible on GitHub by tonight:

- /data/raw/: Contains the original file provided by Rafa.

- /data/processed/: Contains the cleaned version from Sruthi.

## Phase 2: Modeling & Feature Expansion (Next 24 Hours)

- Avinash & Vaastav: Finalize and sign off on the Exploratory Data Analysis (EDA) reports.

- Rafa, Sadiya & Mahesh: Initialize the regression suite, including Simple Linear, Multiple Linear, and Polynomial models.

- Sruthi: Re-open the data sourcing pipeline to identify and merge additional indicators (e.g., expanded WHO/World Bank metrics) to resolve underfitting.

- Saayanth: Prepare to re-scale and encode the incoming batch of new features once Sruthi completes the merge.

### Technical Handoff: From EDA to Modeling Iteration

As the project moves from initial analysis into iterative modeling, the following handoffs are critical for resolving the current feature bottleneck:

#### 1. The EDA Completion Handoff

- Avinash to Modeling Team: Avinash provides the final correlation heatmaps and statistical summaries.

- Objective: Confirm that current features (e.g., Sanitation, Mortality) are insufficient for high-accuracy life expectancy modeling.

#### 2. The Modeling Blocker Handoff

- Rafa, Sadiya & Mahesh to Vaastav: The modeling team reports low $R^2$ scores and high error metrics due to a "thin" dataset.

- Objective: Vaastav triggers a pivot back to the Data Engineering phase to source more robust predictors.

#### 3. The Feature Expansion Handoff

- Vaastav to Sruthi: Request for additional features (e.g., GDP, Schooling, or Immunization rates) to support Polynomial Regression complexity.

- Sruthi to Vrushank: Sruthi merges the new data; Vrushank versions the updated file as expanded_cleaned_data.csv on GitHub.

#### 4. The Re-Engineering Handoff

- Vrushank & Saayanth: The expanded dataset is made available for a second pass of Feature Scaling and One-Hot Encoding .They  have both done it and then the combined best results

- Objective: Ensure the new features are model-ready for tomorrow’s training session

Phase 3: Evaluation & Advanced Modeling (Next 24 Hours)

Avinash & Vaastav: Formally sign off as the Exploratory Data Analysis (EDA) has been completed.

Rafa: Has successfully completed the Multi Linear Regression modeling and baseline performance reporting.

Ravi & Team: The team has officially started evaluating the Multi Linear Regression modeling.

Issa: Has completed the evaluation of the Multi Linear model to determine final accuracy metrics.

Mahesh & Sadiya: Are still working on Linear and Polynomial regression scripts to address previous underfitting issues.

Sruthi, Saayanth, & Vrushank: Conducting advanced research on feature selection and optimization strategies to refine the modeling pipeline.

Technical Handoff: From Baseline Modeling to Evaluation

As the project transitions from initial modeling to rigorous performance assessment, the following handoffs are critical:

- The Modeling Completion Handoff

  - Rafa to Ravi: Rafa provides the completed Multi Linear Regression results for formal validation.

  - Objective: Transition from model training to the Evaluation & Optimization phase.

- The Evaluation Handoff

  - Issa to Vaastav: Issa delivers the final evaluation report for the Multi Linear model.

  - Objective: Use finalized metrics ($R^2$, MAE, RMSE) to set the benchmark for ongoing sessions.

- The Advanced Iteration Handoff

  - Sadiya & Mahesh to Modeling Team: Continuous updates on the progress of Linear and Polynomial regression.

  - Objective: Overcome the "feature-thin" bottleneck identified in Phase 2.

- The Research & Development Handoff

  - Sruthi, Saayanth & Vrushank to Vaastav: Insights from independent research are compiled to guide the final optimization.

  - Objective: Ensure the project stays aligned with Milestone Management goals.

Hourly Milestone Timeline (General)

If a supervisor asks for a timestamped breakdown, here is how the 5 hours are spent:

- Hour 1: Sync & Discussion. 1-hour discussion meeting led by Vaastav to confirm EDA completion and review Rafa’s Multi Linear model results.

- Hour 2-3: Model Execution & Evaluation. Issa and Ravi calculate accuracy metrics; Sadiya and Mahesh continue training Linear and Polynomial models.

- Hour 4: Strategic Research. Sruthi, Saayanth, and Vrushank research optimization techniques to improve future model iterations.

- Hour 5: Review & Documentation. Vaastav reviews the day's progress; Vrushank updates the GitHub repository with evaluation reports.

### Phase 4: Final Evaluation & Optimization (Next 24 Hours)

The project has transitioned into final performance assessments and model refinement based on the latest technical milestones achieved by the team.

Key Progress Milestones:

- EDA Completion: Avinash and Vaastav have formally signed off as the Exploratory Data Analysis (EDA) has been completed.

- Multi Linear Regression: Rafa has successfully completed the Multi Linear Regression modeling and established the baseline performance reports.

- Evaluation Milestones: The evaluating team, led by Issa, has completed evaluating the Multi Linear Regression modeling to determine the final accuracy metrics for the baseline.

- Polynomial Modeling: Mahesh has completed his polynomial regression modeling with the technical guidance and assistance of Vaastav.

- Ongoing Development: Rafa and Sadiya are still working on linear and polynomial regression scripts to continue addressing previous underfitting issues and refine model architecture.

- Strategic Research: The rest of the team (Sruthi, Saayanth, and Vrushank) are conducting advanced research on feature selection and optimization strategies to refine the final modeling pipeline.

Technical Handoff: From Evaluation to Final Optimization

| Handoff Type | Description | Objective |
| --- | --- | --- |
| The Modeling Completion Handoff | Rafa and Mahesh provide completed regression results (Multi Linear and Polynomial) to the evaluation team. | Transition from model training to the final Evaluation & Optimization phase. |
| The Evaluation Handoff | Issa delivers the final evaluation report for the Multi Linear model to Vaastav. | Use finalized metrics ($R^2$, MAE, RMSE) to set the benchmark for the final report. |
| The Research & Development Handoff | Sruthi, Saayanth, and Vrushank compile insights from independent research for Vaastav. | Ensure the project stays aligned with Milestone Management goals and final tuning requirements. |

Hourly Milestone Timeline (General)

If a supervisor asks for a timestamped breakdown, here is how the 5 hours are spent:

- Hour 1: Sync & Discussion. A 1-hour discussion meeting led by Vaastav to confirm EDA completion and review Rafa’s Multi Linear model results.

- Hour 2-3: Model Execution & Evaluation. Issa and Ravi calculate accuracy metrics while Sadiya continues training her regression models.

- Hour 4: Strategic Research. Sruthi, Saayanth, and Vrushank research optimization techniques to improve future model iterations.

- Hour 5: Review & Documentation. Vaastav reviews the day's progress; Vrushank updates the GitHub repository with the new evaluation reports.

## Phase 5: Final Evaluation, Reporting & SDG Alignment (Next 24 Hours)

The project has moved into the final reporting phase, integrating model performance with Sustainable Development Goal (SDG) impact analysis.

### Key Progress Milestones:

- EDA Completion: Avinash and Vaastav have formally signed off as the Exploratory Data Analysis (EDA) has been completed.

- Multi Linear Regression: Rafa has successfully completed the Multi Linear Regression modeling and established baseline performance reports.

- Modeling Achievements: Mahesh and Sadiya have completed their linear and polynomial regression scripts to address previous underfitting issues.

- Evaluation Milestones: Issa has completed the evaluation of the Multi Linear model as well as the linear and polynomial regression evaluation to determine final accuracy metrics.

- Reporting: Ravi has compiled and made the final report of the evaluation, including $R^2$ and RMSE benchmarks.

- SDG Integration: Manoj and Harshita R are actively working on the SDG analytics report to align technical findings with global health targets.

- Strategic Research: The rest of the team (Sruthi, Saayanth, and Vrushank) are conducting advanced research on feature selection and optimization strategies to refine the final modeling pipeline.

### Technical Handoff: From Evaluation to SDG Analytics

| Handoff Type | Description | Objective |
| --- | --- | --- |
| The Evaluation Finalization | Issa and Ravi provide the completed evaluation report and error metrics to the SDG team. | Transition technical metrics into the final SDG Analytics Report. |
| The SDG Impact Handoff | Manoj and Harshita R deliver the draft SDG report to Vaastav. | Align model outcomes with Milestone Management goals and global health indicators. |
| The Research & Development Handoff | Sruthi, Saayanth, and Vrushank compile insights from independent research for Vaastav. | Ensure the project stays aligned with final tuning requirements. |

Hourly Milestone Timeline (General)

If a supervisor asks for a timestamped breakdown, here is how the 5 hours are spent:

- Hour 1: Sync & Discussion. A 1-hour discussion meeting led by Vaastav to confirm EDA completion, review regression results, and delegate SDG reporting tasks.

- Hour 2-3: Evaluation & Analytics. Issa and Ravi finalize evaluation metrics while Manoj and Harshita R begin the SDG analytics report.

- Hour 4: Strategic Research. Sruthi, Saayanth, and Vrushank research optimization techniques to improve future model iterations.

- Hour 5: Review & Documentation. Vaastav reviews the day's progress; Vrushank updates the GitHub repository with the final evaluation and SDG reports.

### Phase 5 Report: Final Evaluation, Reporting & SDG Alignment

The project has moved into the final reporting phase, integrating model performance with Sustainable Development Goal (SDG) impact analysis.

- EDA Completion: Avinash and Vaastav have formally signed off on the completed EDA.

- Modeling Milestones: Rafa finished the Multi Linear baseline , while Mahesh and Sadiya completed the linear and polynomial regression scripts.

- Evaluation Status: The team officially started and completed the evaluation of all models (Multi Linear, Linear, and Polynomial).

- Final Reporting: Ravi generated the final evaluation report while Manoj and Harshita R finalized the SDG impact analysis.

- Project Conclusion: Vrushank has updated the GitHub README, and the project is now finished.

### Hourly Milestone Timeline

- Hour 1: Sync & Discussion. 1-hour discussion meeting led by Vaastav to confirm EDA completion and review regression results.

- Hour 2-3: Evaluation & Analytics. Issa and Ravi finalize evaluation metrics while Manoj and Harshita R complete the SDG analytics report.

- Hour 4: Strategic Research. Sruthi, Saayanth, and Vrushank research optimization techniques for final pipeline refinement.

- Hour 5: Review & Documentation. Vaastav reviews the day's progress; Vrushank updates the GitHub repository with final reports.